## Project Timeline
PROJECT TIMELINE
PROJECT TITLE |  | CST8248 Project |  | COMPANY NAME |  | Team 23
PROJECT MANAGER |  | Israt Karim, Nick Forgues, Chadayne Spenceclarke(?) |  | DATE |  | 9/26/2020
PHASE |  |  | DETAILS
|  |  |  | SEP |  |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
| PROJECT WEEK: |  | (First Monday of each week) | 7 | 14 |  | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14
1 | Project Conception and Initiation |  | - Brainstorming
- Research
-Planning
- Initiation
2 | Private Cloud |  | - Configue jump server
- Deploy 2 VSphere Hosts
- HTTP
|  |  | - DNS | [16 empty] | P
|  |  | - LDAP or AD | [16 empty] | R
|  |  | -iSCSI Target | [16 empty] | O
|  |  | -iSCSI Initiator | [16 empty] | J
|  |  | -File Server | [16 empty] | E
|  |  | -Enterprise Backup | [16 empty] | C
|  |  | -Inventory Management System | [16 empty] | T
-WAC
|  |  | -Deploy client machines | [16 empty] | D
|  |  | - Ensure connectivity | [16 empty] | E
3 | Public Cloud |  | - Azure Interface | [16 empty] | A
|  |  | - Governance in public cloud | [16 empty] | D
|  |  | - PostGreSQL | [16 empty] | L
|  |  | -Web Server connected to database | [16 empty] | I
|  |  | -Network Security Group | [16 empty] | N
4 | Value Added |  | - | [16 empty] | E
-
-
5 | Testing and Project Close |  | - Testing
-Technical Report
- Project End